## Sheet1
PSP Defect Recording Log
Student | Yu-Hong.Jhuo
Program | PR280
Instructor | Michael, Luofeng
Date | No. | Type | Inject | Remove | Fix Time | Fix Ref | Description
2018-09-12 | 1 | MA | coding | testing | 1 mins | NA | forget to reset this.lowerLimit in setup()
2018-09-12 | 2 | MA | coding | testing | 1 mins | NA | forget to reset this.higherLimit in setup()
2018-09-12 | 3 | MI-OM | coding | testing | 2 mins | NA | Forget to add return response when the user responds "Correct!"
2018-09-12 | 4 | WA | coding | testing | 1 mins | NA | (this.upperLimit - this.lowerLimit) / 2) should be (this.upperLimit + this.lowerLimit) / 2)
2018-09-12 | 5 | MI-TY | coding | testing | 1 mins | NA | miss $ for literal template
2018-09-12 | 6 | WC | coding | testing | 5 mins | NA | miss a condition of upperLimit is lower than lowerLimit
2018-09-12 | 7 | MI-OM | design | testing | 5 mins | NA | should create a method app3Setup() for app3
2018-09-12 | 8 | MI-OM | coding | testing | 4 mins | NA | should create a method to pass user's reponse to guesser3
2018-09-12 | 9 | MI-OM | coding | testing | 3 mins | NA | event handler for input button should change to replyUserResponse
2018-09-12 | 10 | MI-OM | coding | testing | 3 mins | https://vuejs.org/v2/guide/forms.html | forget to add v-model= "userResponse" into <input>

## Instructions
PSP Defect Recording Log Instructions
Purpose | - Use this form to hold data on the defects that you find and correct.
- These data are used to complete the Project Plan Summary form.
General | - Record each defect separately and completely.
- If you need additional space, use another copy of the form.
Header | - Enter your name and the date.
- Enter the program name and number.
- Enter the instructor’s name and the programming language you are using.
Project | - Give each program a different name or number.
- For example, record test program defects against the test program.
Date | Enter the date on which you found the defect.
Number | - Enter the defect number.
- For each program or module, use a sequential number starting with 1 (or 001, etc.).
Type | - Enter the defect type from the defect type list summarized in the top left corner of the form.
- Use your best judgment in selecting which type applies.
Inject | - Enter the phase when this defect was injected.
- Use your best judgment.
Remove | Enter the phase during which you fixed the defect. (This will generally be the phase when you found the defect.)
Fix Time | - Enter the time that you took to find and fix the defect.
- This time can be determined by stopwatch or by judgment.
Fix Ref. | - If you or someone else injected this defect while fixing another defect, record the number of the improperly fixed defect.
- If you cannot identify the defect number, enter an X.
Description | Write a succinct description of the defect that is clear enough to later remind you about the error and help you to remember why you made it.
A PSP Defect Type Standard
Type Number | Type Name | Description
10 | Documentation | Comments, messages
20 | Syntax | Spelling, punctuation, typos, instruction formats
30 | Build, Package | Change management, library, version control
40 | Assignment | Declaration, duplicate names, scope, limits
50 | Interface | Procedure calls and references, I/O, user formats
60 | Checking | Error messages, inadequate checks
70 | Data | Structure, content
80 | Function | Logic, pointers, loops, recursion, computation, function defects
90 | System | Configuration, timing, memory
100 | Environment | Design, compile, test, or other support system problems